## Sheet1
Where Are We?

#	Title	Who	Beta Posted	Production	Review Status
1	Why FP? Why Haskell?	shared	posted
2	Getting started	shared	posted
3	Types and Functions	shared	posted
4	Defining Types, Streamlining	shared	posted
5	Functional Programming	bos	posted
6	Writing a Library	bos	posted
7	Using Typeclasses	jg/bos	posted		JSON PART NEEDS REVIEW; john's part beta reviewed 7/3/2008, 3/11/2008
8	I/O	jg	posted	07/08/08	beta reviewed 7/7/2008, 3/11/2008
9	Case study: Regular Expressions	bos	posted
10	I/O: DSL for searching FS	bos	posted
11	Binary data	bos	posted
12	QuickCheck	dons	posted
13	Barcode recognition	bos	posted
14	Data structures	jg	posted		LAST PART NEEDS REVIEW; john's part beta reviewed 7/7/2008, 3/11/2008
15	Monads	bos	posted
16	Monad case study: fs searcher	bos	posted
17	Monad transformers	bos	posted
18	Using Parsec	jg	posted		alpha reviewed 5/08/2008 of john's part only
19	FFI	dons
20	Error handling	jg	posted		john's part done (alpha)
21	Systems programming	jg	posted	07/08/08	beta reviewed 7/8/2008
22	Databases	jg	posted	07/08/08	beta reviewed 7/8/2008
23	Web client	jg	posted	07/08/08	beta reviewed 7/8/2008
24	GUI: gtk2hs	jg	posted	07/08/08	beta reviewed 7/8/2008
25	Concurrent/Parallel basics	bos	posted
26	Profiling	dons
27	Advnaced Haskell	dons	posted			need a place for MPTCs, fundeps if we eliminate this
28	Sockets, Syslog	jg	posted	on hold pending ch26 completion	beta reviewed 7/8/2008
29	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	posted
B	Escapes	bos	posted

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	Err:504	Err:504
Half of chapters: November 15, 2007		bos	14	Err:504	Err:504
Complete first draft: March 1, 2008		dons	4	Err:504	Err:504
Complete final draft: April 1, 2008		jg	10	Err:504	Err:504

		TOTAL	31	28	90%

who	1st Draft/Alpha
.*shared.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*bos.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*dons.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*jg.*	.*(done|ready|posted).*