## Sheet1
Where Are We?

#	Title	Who	1st Draft/Alpha	Beta Posted	Review Status
1	Why FP? Why Haskell?	shared
2	Getting started	shared	posted (bos)	posted
3	Types and Functions	shared	posted (bos)	posted
4	Defining Types, Streamlining	shared	posted (bos)	posted
5	Functional Programming	bos	ready
6	Writing a Library	bos	ready
7	Using Typeclasses	jg	posted	posted	beta reviewed 3/11/2008
8	I/O	jg	posted	posted	beta reviewed 3/11/2008
9	Case study: Regular Expressions	bos	posted	posted
10	I/O: DSL for searching FS	bos	posted
11	Binary data	bos	posted
12	QuickCheck	dons
13	Barcode recognition	bos	ready
14	Data structures	jg	posted
15	Monads	bos	ready
16	Monad case study: fs searcher	bos
17	Monad transformers	dons
18	Using Parsec	jg	ready
19	FFI	dons
20	Error handling	dons
21	Systems programming	jg	ready			pending ability to remove redundant material and integrate rest into other chapters
22	Databases	jg	ready
23	Web client	jg	ready
24	GUI: gtk2hs	jg				a target to eliminate if we are still tight on page count at the end
25	Concurrent/Parallel basics	jg/dons
26	Profiling	dons
27	Advnaced Haskell	dons				need a place for MPTCs, fundeps if we eliminate this
28	Sockets, Syslog	jg	ready
29	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	posted	posted
B	Escapes	bos	posted	posted

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	3	75%
Half of chapters: November 15, 2007		bos	11	9	82%
Complete first draft: March 1, 2008		dons	7	0	0%
Complete final draft: April 1, 2008		jg	10	8	80%

		TOTAL	31	20	65%

who	1st Draft/Alpha
.*shared.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*bos.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*dons.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*jg.*	.*(done|ready|posted).*