## Sheet1
Where Are We?

#	Title	Who	1st Draft/Alpha	Beta Posted	Review Status
1	Why FP? Why Haskell?	shared
2	Getting started	shared	posted (bos)	posted
3	Types and Functions	shared	posted (bos)	posted
4	Defining Types, Streamlining	shared	posted (bos)	posted
5	Functional Programming	bos	ready
6	Writing a Library	bos/dons
7	Using Typeclasses	jg	posted	posted
8	I/O	jg	posted	posted
9	Case study: Regular Expressions	bos	posted
10	I/O: DSL for searching FS	bos	posted
11	Binary data	bos	posted
12	QuickCheck	dons
13	Barcode recognition	bos	posted
14	Data structures	jg	posted
15	Monads	bos	ready
16	Monad case study: fs searcher	bos
17	Monad transformers	dons
18	Using Parsec	jg	ready
18a/19	Further Adventures in Parsing	bos
20	FFI	dons
21	Error handling	dons
22	Systems programming	jg	ready
23	Databases	jg	ready
24	Web client	jg
25	GUI: gtk2hs	bos
26	Data mining	?
27	Concurrent/Parallel basics	jg/dons
29	Advanced Concurrent/Parallel	dons
29	Concurrency: lockless DB, STM	dons
30	Profiling	dons
31	Advnaced Haskell	dons
32	Sockets, Syslog	jg	ready
33	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	posted	posted
B	Escapes	bos	posted	posted
C?	POSIX?	jg
D?	HUGS?	jg
E?	Data.Typeable?	jg

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	3	75%
Half of chapters: November 15, 2007		bos	13	8	62%
Complete first draft: March 1, 2008		dons	10	0	0%
Complete final draft: April 1, 2008		jg	12	7	58%

		TOTAL	38	18	47%

who	1st Draft/Alpha
.*shared.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*bos.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*dons.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*jg.*	.*(done|ready|posted).*