## Sheet1
Where Are We?

#	Title	Who	1st Draft/Alpha	Beta Posted	Review Status
1	Why FP? Why Haskell?	shared
2	Getting started	shared	posted (bos)	posted
3	Types and Functions	shared	posted (bos)	posted
4	Defining Types, Streamlining	shared	posted (bos)	posted
5	Functional Programming	bos	ready
6	Writing a Library	bos/dons
7	Using Typeclasses	jg	posted	posted
8	I/O	jg	posted	posted
9	Case study: Regular Expressions	bos	posted
10	I/O: DSL for searching FS	bos	posted
11	Binary data	bos	posted
12	QuickCheck	dons
13	Barcode recognition	bos	posted
14	Data structures	jg	posted
15	Monads	bos	ready
16	Monad case study: fs searcher	bos
17	Monad transformers	dons
18	Using Parsec	jg	ready
19	FFI	dons
20	Error handling	dons
21	Systems programming	jg	ready
22	Databases	jg	ready
23	Web client	jg
24	GUI: gtk2hs	bos
25	Data mining	?
26	Concurrent/Parallel basics	jg/dons
27	Advanced Concurrent/Parallel	dons
28	Concurrency: lockless DB, STM	dons
29	Profiling	dons
30	Advnaced Haskell	dons
31	Sockets, Syslog	jg	ready
32	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	posted	posted
B	Escapes	bos	posted	posted
C?	POSIX?	jg
D?	HUGS?	jg
E?	Data.Typeable?	jg

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	3	75%
Half of chapters: November 15, 2007		bos	12	8	67%
Complete first draft: March 1, 2008		dons	10	0	0%
Complete final draft: April 1, 2008		jg	12	7	58%

		TOTAL	37	18	49%

who	1st Draft/Alpha
.*shared.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*bos.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*dons.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*jg.*	.*(done|ready|posted).*