## Sheet1
Where Are We?

#	Title	Who	1st Draft	Reviewed	2nd Draft
1	Why FP? Why Haskell?	shared	started
2	Getting started	shared	done (bos)	posted
3	Syntax, type system basics	shared	done (bos)	posted
4	Functional Programming	shared	done (bos)	ready
5	Write a library	bos/dons
6	Typeclasses	jg	done	posted	written
7	I/O	jg	done	posted
8	File name matching, regexps	bos	done	ready
9	I/O: DSL for searching FS	bos	done	ready
10	Barcode recognition	bos	done	ready
11	QuickCheck	dons
12	Binary files and formats	bos	done
13	Data structures	jg	done	ready
14	Monads	bos
15	Monad case study: fs searcher	bos
16	Monad transformers	dons
17	Parsec	jg	done	ready
17.5	parsing a bioinformatics format	bos
18	FFI	dons
19	Error handling	dons
20	Systems programming	jg	done	ready
21	Databases	jg	done	ready
22	Web client	jg
23	GUI: gtk2hs	bos
24	Data mining	?
25	Concurrent/Parallel basics	jg/dons
26	Advanced Concurrent/Parallel	dons
27	Concurrency: lockless DB, STM	dons
28	Profiling	dons
29	Advnaced Haskell	dons
30	Sockets, Syslog	jg
31	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	done	posted
B	Escapes	bos	done	posted
C?	POSIX?	jg
D?	HUGS?	jg
E?	Data.Typeable?	jg

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	3	75%
Half of chapters: November 15, 2007		bos	12	6	50%
Complete first draft: March 1, 2008		dons	10	0	0%
Complete final draft: April 1, 2008		jg	12	6	50%

		TOTAL	32	15	47%

who	1st Draft
.*shared.*	.*done.*
who	1st Draft
.*bos.*	.*done.*
who	1st Draft
.*dons.*	.*done.*
who	1st Draft
.*jg.*	.*done.*