## Sheet1
Where Are We?

#	Title	Who	1st Draft/Alpha	Beta Posted	Review Status
1	Why FP? Why Haskell?	shared	posted	posted
2	Getting started	shared	posted (bos)	posted
3	Types and Functions	shared	posted (bos)	posted
4	Defining Types, Streamlining	shared	posted (bos)	posted
5	Functional Programming	bos	posted	posted
6	Writing a Library	bos	posted	posted
7	Using Typeclasses	jg	posted	posted	beta reviewed 3/11/2008
8	I/O	jg	posted	posted	beta reviewed 3/11/2008
9	Case study: Regular Expressions	bos	posted	posted
10	I/O: DSL for searching FS	bos	posted	posted
11	Binary data	bos	posted	posted
12	QuickCheck	dons	ready
13	Barcode recognition	bos	posted
14	Data structures	jg	posted	posted	alpha reviewed 3/25/2008
15	Monads	bos	posted	posted
16	Monad case study: fs searcher	bos	posted	posted
17	Monad transformers	bos	posted	posted
18	Using Parsec	jg	posted		alpha reviewed 5/08/2008 of john's part only
19	FFI	dons
20	Error handling	jg	ready		john's part done
21	Systems programming	jg	posted		alpha reviewed 5/8/2008
22	Databases	jg	posted	posted	alpha reviewed 4/01/2008
23	Web client	jg	posted		alpha reviewed 5/8/2008
24	GUI: gtk2hs	jg	posted		alpha reviewed 5/8/2008
25	Concurrent/Parallel basics	bos
26	Profiling	dons
27	Advnaced Haskell	dons				need a place for MPTCs, fundeps if we eliminate this
28	Sockets, Syslog	jg	posted		alpha reviewed 5/8/2008
29	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	posted	posted
B	Escapes	bos	posted	posted

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	4	100%
Half of chapters: November 15, 2007		bos	13	11	85%
Complete first draft: March 1, 2008		dons	4	1	25%
Complete final draft: April 1, 2008		jg	10	10	100%

		TOTAL	31	26	84%

who	1st Draft/Alpha
.*shared.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*bos.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*dons.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*jg.*	.*(done|ready|posted).*