## Sheet1
Where Are We?

#	Title	Who	1st Draft/Alpha	Beta Posted	Review Status
1	Why FP? Why Haskell?	shared	posted	posted
2	Getting started	shared	posted (bos)	posted
3	Types and Functions	shared	posted (bos)	posted
4	Defining Types, Streamlining	shared	posted (bos)	posted
5	Functional Programming	bos	posted	posted
6	Writing a Library	bos	posted	posted
7	Using Typeclasses	jg	posted	posted	beta reviewed 7/3/2008, 3/11/2008
8	I/O	jg	posted	posted	beta reviewed 7/7/2008, 3/11/2008
9	Case study: Regular Expressions	bos	posted	posted
10	I/O: DSL for searching FS	bos	posted	posted
11	Binary data	bos	posted	posted
12	QuickCheck	dons	posted	posted
13	Barcode recognition	bos	posted	posted
14	Data structures	jg	posted	posted	LAST PART NEEDS REVIEW; john's part beta reviewed 7/7/2008, 3/11/2008
15	Monads	bos	posted	posted
16	Monad case study: fs searcher	bos	posted	posted
17	Monad transformers	bos	posted	posted
18	Using Parsec	jg	posted	posted	alpha reviewed 5/08/2008 of john's part only
19	FFI	dons
20	Error handling	jg	posted	posted	john's part done (alpha)
21	Systems programming	jg	posted	posted	beta reviewed 7/8/2008
22	Databases	jg	posted	posted	beta reviewed 7/8/2008
23	Web client	jg	posted	posted	beta reviewed 7/8/2008
24	GUI: gtk2hs	jg	posted	posted	beta reviewed 7/8/2008
25	Concurrent/Parallel basics	bos	posted	posted
26	Profiling	dons
27	Advnaced Haskell	dons	posted	posted		need a place for MPTCs, fundeps if we eliminate this
28	Sockets, Syslog	jg	posted	posted	beta reviewed 7/8/2008
29	Reverse HTTP Proxy	bos
A	Installation of GHC	bos	posted	posted
B	Escapes	bos	posted	posted

DEADLINES		Who	Total Chap.	# 1st Done	% Done
First 2 chapters: July 1, 2007		shared	4	4	100%
Half of chapters: November 15, 2007		bos	13	12	92%
Complete first draft: March 1, 2008		dons	4	2	50%
Complete final draft: April 1, 2008		jg	10	10	100%

		TOTAL	31	28	90%

who	1st Draft/Alpha
.*shared.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*bos.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*dons.*	.*(done|ready|posted).*
who	1st Draft/Alpha
.*jg.*	.*(done|ready|posted).*